## Sheet1
Week | Tasks/Phases | Milestones
1 | Research and Planning | Finalize tech stack, architectural design, and workflows.
1 | - Research technologies for each layer (React.js, Django/.NET, Llama, Pinecone). | Draft complete technical and architectural diagrams.
1 | - Define system architecture and finalize schema for database components.
2 | Frontend Setup | Basic frontend UI functionality, chat interface, and project repository setup.
2 | - Set up the React.js environment and initialize code editor integration. | Delivering a working skeleton of the frontend project.
3 | Frontend Functionalities | User interaction components (syntax highlighting, input processing) completed.
3 | - Create user interface, integrate Monaco Editor, enable syntax highlighting and responsive design. | Working frontend capable of sending test queries to mock APIs.
4 | Backend Layer Setup | Backend initialized with user authentication and API routing.
4 | - Set up Django/.NET Core project, configure authentication (OAuth2/JWT). | Complete the setup of secure user authentication and profile management.
5 | API Gateway and Task Orchestrator Integration | API routing and basic user query handling functional.
5 | - Implement centralized API Gateway to direct all user queries. | Task Orchestrator operational with query preprocessing.
5 | - Enable task orchestration for routing requests (mock implementations).
6 | LLM Inference Integration | End-to-end integration with the selected LLM and preprocessing pipelines.
6 | - Deploy Llama (Code Llama) or alternative on a GPU-enabled instance. | LLM generates basic responses with query preprocessing/postprocessing operational.
7 | Knowledge Base Module | Integrated retriever logic and response aggregation completed.
7 | - Set up vector search (Pinecone/Weaviate), integrate Elasticsearch. | Working knowledge module for retrieving and merging relevant snippets with LLM-generated responses.
8 | Database Layer Implementation | Database schema finalized and CRUD operations for major components established.
8 | - Configure PostgreSQL/MongoDB schemas for users, problems, and solutions. | Store user query logs and track usage in the database.
9 | Monitoring, Deployment, and CI/CD | Monitoring system, CI/CD pipeline, and scalable hosting implemented.
9 | - Implement performance monitoring with Prometheus and Grafana. | Hosted platform with automated deployments and alert systems.
10 | Optional Real-Time Features & Security Enhancements | Enable WebSockets or SignalR-based real-time updates, finalize additional security measures.
10 | - Build websocket-based features (real-time typing suggestions, instant update).
10 | - Perform final security audit (rate-limiting, encryption, access control). | Final system stress test and validation before deployment.